## Doc Number
Reference | ComReg 23/102c

## Hypothetical Sample Report
Exchange Name | Exchange Code | Stop Sell Notice Date | Number of in-scope premises in exchange | Number of in-scope premises in exchange passed by Modern Infrastructure at Stop Sell notice date | Percentage of in-scope premises in exchange passed by Modern Infrastructure at Stop Sell notice date | Stop Sell Date (Milestone 1) | Number of in-scope premises in exchange passed by Modern Infrastructure at Stop Sell date | Percentage of in scope premises in exchange passed with Modern Infrastructure at Stop Sell date | Number of in scope premises in exchange passed with Modern Infrastructure | Percentage of in scope premises passed with Modern Infrastructure | Number of in scope premises with active legacy-based services | Percentage of in scope premises with active legacy copper-based services | Number of in scope premises with TLSs | Number of exempt users registered | Modern Infrastructure Rollout Complete date and Switch-off Phase 1 notice date (Milestone 2) | Switch-off Phase 1 forecast date; | Switch-off Phase 1 confirmation notice date | Switch-off Phase 1 complete and Switch-off Phase 2 notice date (Milestone 3) | Switch-off Phase 2 forecast date | Switch-off Phase 2 confirmation notice date | Switch-off Phase 2 complete date (Milestone 4) | Decommission date
Ashbourne | ABE | 2022-12-30 | 5000 | 3500 | 70% | 2023-06-30 | 4000 | 80% | 5000 | 100% | 300 | 6% | 10 | 80 | 2025-05-01 | 2026-05-31 | 2026-02-28
Abbeyknockmoy | ABK |  | 600 |  | 0% |  |  | 0% | 600 | 100% | 0 | 0% | 0 | 30 | 2023-08-31 | 2024-10-31 | 2024-05-31 | 2024-10-31 | 2025-04-30 | 2025-01-31 | 2025-04-30 | 2025-05-31
Cork Airport Ind Est | ABP | 2023-05-31 | 30 | 25 | 83.33% | 2023-11-30 | 27 | 90% | 30 | 100% | 3 | 10% | 0 | 3 | 2024-01-31 | 2025-01-31 | 2024-10-31 | 2025-01-31 | 2026-05-31 | 2026-02-28
Abbeyleix | ABX | 2024-06-15 | 2000 | 1500 | 75% | 2024-12-15 | 1600 | 80% | 2000 | 100% | 500 | 25% | 0 | 2 | 2026-02-28 | 2027-02-28
Athboy | ABY | 2024-07-31 | 2100 | 1500 | 71.43% | 2025-01-31 | 1700 | 80.95% | 2070 | 98.57% | 400 | 19.05% | 10 | 20 | 2026-03-15 | 2027-06-30
Aclare | ACE | 2025-09-30 | 500 | 320 | 64% | 2026-03-30 | 400 | 80% | 400 | 80% | 90 | 18% | 0 | 0
Aughnacliffe | ACF | 2025-12-31 | 400 | 250 | 62.5% | 2026-06-30 |  |  | 270 | 67.5% | 250 | 62.5%
Annascaul | ACL |  | 600 |  | 0% |  |  |  | 50 | 8.333% | 480 | 80%